## FR
A
[26 empty] | DAILY DRILLING REPPORT | [18 empty] | N°: |  |  | 51 | [11 empty] | Date: |  |  |  | 11/05/2013
|  |  |  | Depth @ 24h : |  |  |  | 9582 |  | ft /TVD: |  | 9582 |  |  | ft | PROGRESS : | [7 empty] | ft | in |  |  |  | h | [9 empty] | Last Casing/ Liner : | [6 empty] | 7" |  |  | 32 # C95 TENARIS | [7 empty] | AT: |  | 9450 |  |  | ft, | Top AT: |  |  |  | 5556 |  | ft
N° | C | R |  |  | BIT |  | TYPE |  | SERIAL | NOZZELES | [8 empty] | TFA |  | HSI |  |  | WOB(T) |  |  |  | RPM |  |  |  |  | Flow (gpm) |  | Pressure (psi) |  |  |  | Progress (ft) |  |  | Hrs (h) |  | Cumulative | [7 empty] | IADC DULL GRADING | [10 empty] | DEVIATION
|  | N° |  |  | SIZE | [13 empty] | (in²) |  | hp/in² |  |  | Min |  | Max |  | Min |  |  | Max | [12 empty] | (ft) |  |  |  |  | (h) |  |  | 1 | 2 |  | 3 | 4 | 5 |  | 6 | 7 | 8 |  | Depth |  |  | incl |  |  | Azim. |  | TVD
[63 empty] | 9350' |  |  | 1˚
MUD TYPE: |  | NC FLO | [15 empty] | WEIGHT: |  |  |  | 8.8 | [7 empty] | MUD CLEANER SERVICE = Hours | [32 empty] | PITS | [5 empty] | Volumes (bbl)
F.API: | 6 |  | FUNNEL: |  |  |  | 42 | Y.Point: |  | 16 | App. Vis: | [5 empty] | PV: |  | 11 |  |  | F.HPHT: | [21 empty] | Shakers: | [10 empty] | Lost Circ: | [7 empty] | Active | [5 empty] | 325
PH: | 9.5 |  | GEL 10': |  |  |  | 8 | GEL 10': |  | 6 | M.B.T. PPB: 12.5 |  |  | 6 |  |  | %KCL: |  | 4 |  |  | %W: |  |  |  | 98 |  |  |  | CENTRIFUGE SERVICE | [13 empty] | Mud Cleaner: | [10 empty] | Behind Csg: | [7 empty] | Reserve | [5 empty] | 685
[30 empty] | N° |  | Model | [5 empty] | Hours | [5 empty] | S.C.E. Losses | [10 empty] | Other (Hole): | [7 empty] | Kill Mud
Pf: | 0.25 |  | Cacl2: |  |  |  |  | %Solids: |  | 2 | %Sand: | [5 empty] | Ca++: |  | 100 |  |  | NaCI |  |  |  | 0 g/l |  |  |  | 1 |  | BRAND | [11 empty] | Tripping: | [10 empty] | Lost Hole: | [7 empty] | Hole | [5 empty] | 532
Encapsulation:
MF: | 0.45 |  | CL- g/l : |  |  |  | 23 | %LGS: |  | 1.11 | %HGS: | [5 empty] | E-Lime: |  |  |  |  | Cake : |  |  |  | 1 | [17 empty] | Lost Surf: | [6 empty] | 20 |  |  |  | Dumped:
TIMING |  | OPERATION DESCRIPTION | [17 empty] | CODE |  |  | Initial Depth (ft) |  |  |  | Final Depth (ft) |  |  |  |  | Company |  |  | Rate |  | MUD PRODUCTS | [5 empty] | USED |  |  | STORED |  |  |  | UNIT |  | Down hole eqts | [5 empty] | SERIAL | [7 empty] | HOURS
00:00 | 00:15 | Cont Rig up HALIBURTON logging tools Run N˚ 1 ( GR - CBL - VDL - CCL ) | [17 empty] | LOG | [11 empty] | HALIBURT |  |  | T2 |  | SOD.CHLORIDE | [8 empty] | 27 |  |  |  | 1000kg |  | Jar
00:15 | 05:30 | Logging Run N01 ( GR - CBL - VDL - CCL ) | [17 empty] | LOG | [11 empty] | HALIBURT |  |  | T2 |  | Caustic soda | [8 empty] | 85 |  |  |  | 25kg |  | Monel
05:30 | 06:00 | Rig up HALIBURTON logging tools Run N02 ( CAST V ) | [17 empty] | LOG | [11 empty] | HALIBURT |  |  | T2 |  | NUT PLUG (MEDIUM) | [8 empty] | 160 |  |  |  | 25kg |  | Shock Tool
06:00 | 13:00 | Logging Run N02 ( CAST V ) | [17 empty] | LOG | [11 empty] | HALIBURT |  |  | T2 |  | LIME | [8 empty] | 76 |  |  |  | 25kg |  | BHA Components
13:00 | 13:30 | Rig Down HALIBURTON Tools | [17 empty] | LOG | [11 empty] | HALIBURT |  |  | T2 |  | SODA ASH | [8 empty] | 40 |  |  |  | 25kg
13:30 | 15:30 | Pick up Cup Tester and Test BOP: * Hydril 500/2500Psi OK | [17 empty] | TBOP | [11 empty] | ENTP |  |  | T2 |  | BARITE | [12 empty] | 1500kg |  | BHA |  | Item | [7 empty] | Jts |  |  | Len (ft) |  |  | I.D (in) |  | O.D (in)
|  | * Pipe Rams, Chock & Kill lines and Chock manifold 500/4000Psi OK | [34 empty] | NC-CARB M | [8 empty] | 1 |  |  |  | 1000kg |  | 19 |  | Bottom nose | [7 empty] | 1 |  |  | 0.50 |  |  |  |  | 4.5
15:30 | 17:45 | HPJSM and Pick up gun barrels TCP N01 | [17 empty] | DST |  |  | 00 |  |  |  | 186 |  |  |  |  | SCHLUMB |  |  | T1 |  | NUT PLUG (FINE) | [8 empty] | 120 |  |  |  | 25kg |  | 19 |  | High shot density | [7 empty] | 18 |  |  | 189.02 |  |  |  |  | 4.5
17:45 | 24:00 | RIH guns barrels TCP N01 Precautionary | [17 empty] | DST |  |  | 186 |  |  |  | 4459 |  |  |  |  | SCHLUMB |  |  | T1 |  | NC-CARB F | [12 empty] | 1000kg |  | 19 |  | Drop Ball FH | [7 empty] | 1 |  |  | 4.80 |  |  | 1.20 |  | 3.06
[37 empty] | NC-CARB M | [12 empty] | 1000kg |  | 19 |  | Tubing | [7 empty] | 1 |  |  | 30.87 |  |  | 2.44 |  | 2.88
[37 empty] | INHABI L | [8 empty] | 5 |  |  |  | 55gal |  | 19 |  | Long Slot Debris Sub | [7 empty] | 1 |  |  | 1.72 |  |  | 2.50 |  | 2.88
[37 empty] | Clay Sure | [8 empty] | 4 |  |  |  | 55gal |  | 19 |  | Cross Over | [7 empty] | 1 |  |  | 2.79 |  |  | 2.25 |  | 3.5
[37 empty] | MICA(FINE) | [8 empty] | 40 |  |  |  | 25kg |  | 19 |  | DC | [7 empty] | 3 |  |  | 92.92 |  |  | 2.25 |  | 4.75
[37 empty] | MICA(MEDIUM) | [8 empty] | 40 |  |  |  | 25kg |  | 19 |  | RA Marker Sub | [7 empty] | 1 |  |  | 1.67 |  |  | 2.25 |  | 5
|  | AFTER MIDNIGHT | [34 empty] | XAN-D | [8 empty] | 6 |  |  |  | 25kg |  | 19 |  | DC | [7 empty] | 15 |  |  | 464.65 |  |  | 4.75 |  | 2.25
00:00 | 05:00 | Cont RIH guns barrels TCP N01 Precautionary f/4459' t/9306' | [34 empty] | NC- PAC UL | [8 empty] | 42 |  |  |  | 25kg |  | 19 |  | DP 3"1/2 | [7 empty] | 117 |  |  | 3577.04 |  |  | 2.25 |  | 3.50
05:00 | 05:45 | Rig up HALLIBURTON logging tools ( GR - CCL ) for TCP correlation | [34 empty] | NUT PLUG (COARSE) | [8 empty] | 120 |  |  |  | 25kg |  | 19 |  | Cross Over | [7 empty] | 1 |  |  | 3.87 |  |  | 2.5 |  | 5.00
05:45 | 06:00 | RIH ( GR - CCL ) logging tools in porgress | [34 empty] | NC- CIDE | [8 empty] | 4 |  |  |  | 55 gal |  | 19 |  | DP 5" + Pup joint | [7 empty] | 158 |  |  | 4937 |  |  | 4.28 |  | 5.00
[37 empty] | NC LUBE | [8 empty] | 2 |  |  |  | 55gal |  |  |  | TOTAL LENGTH | [10 empty] | 9306.85
[37 empty] | MICA(COARSE) | [8 empty] | 145 |  |  |  | 25kg
[37 empty] | POT.CHLORIDE | [12 empty] | 1000kg
[37 empty] | RIG WATER | [5 empty] | 950 | [6 empty] | m3
[28 empty] | Current Operations | [10 empty] | PUMPS
DRILLING WITH TOP DRIVE | [38 empty] | PUMP |  |  | OPER |  | SPM |  |  |  | SPP (psi)
Daily NPT = 0 hr / Cumulative NPT = 0.42days | [38 empty] | P1 |  |  | SCR |  | 20
NPT distribution : ENTP (13.25hrs) / Hole problems (hrs) / HALLIBURTON (2.25hrs) / SCHLUMBERGER (1hrs) | [38 empty] | P1 |  |  | SCR |  | 40
[39 empty] | P2 |  |  | SCR |  | 20
[39 empty] | P2 |  |  | SCR |  | 40
R1: Test Upstream DST Equipement 4000psi & 2 Flare Lines 630psi OK. | [27 empty] | LITHOLOGY - ROP ft/hr
[28 empty] | From ft |  |  |  |  | To ft |  |  | Total Int ft |  |  |  | wc |  | woc |  |  | Stage
[28 empty] | 8495 |  |  |  |  | 8732 |  |  | 237 |  |  |  | 13.13 |  | 9.11 |  |  | U.Mamuniyat
[28 empty] | 8732 |  |  |  |  | 9105 |  |  | 373 |  |  |  | 10.81 |  | 18.18 |  |  | Melaz Shugran
[28 empty] | 9105 |  |  |  |  | 9398 |  |  | 293 |  |  |  | 13.95 |  | 20.17 |  |  | Hawaz
[28 empty] | 9398 |  |  |  |  | 9455 |  |  | 57 |  |  |  | 16.28 |  | 20.75 |  |  | Hassawna
[28 empty] | 9455 |  |  |  |  | 9582 |  |  | 127 |  |  |  | 9.76 |  | 11.36 |  |  | Basement
PLANNED OPERATION: | [5 empty] | DST N01 | [18 empty] | Last BOP'S TEST : | [8 empty] | 11/05/2013 | [6 empty] | Daily Cost: | [5 empty] | 50886.935
[25 empty] | Accident Free Days : | [8 empty] | 543 | [6 empty] | Cumulative cost: | [5 empty] | 6285407.9321 |  |  |  |  | US$ | [12 empty] | Drilling engineer:
REQUIREMENTS: | [24 empty] | Last Safety Meeting : | [8 empty] | 11/05/2013 | [30 empty] | Altumi: (18)
[25 empty] | Planned Day : | [39 empty] | Geologist: Krimo: (27)
[25 empty] | Actual Day : | [8 empty] | 52 | [30 empty] | Almehdi: (28) // Benbellil: (09)
Superintendent:
Latreche: (48)

## Daily Cost
DETAIL OF CONTRACT SERVICES/EQUIPMENT PROVIDED | Lump Sum - Day Rate | Unit | DISCOUNT
|  |  |  | Qty | daily cost
DRILLING RIG - ENTP
Operating Rate | 1479.16 | $ |  | 8.5 | 12572.86
Stand-by Rate | 1331.25 | $ |  | 15.5 | 20634.375
Reduced Performance Rate | 961.45 | $ |  |  | 0
Force Majeur Rate | 887.5 | $ |  |  | 0
Stacked Rate |  |  |  | 24
ADDITIONAL SERVICES
Additional Catering (> 12 persons ) | 60 | DR | x person | 29 | 1740
TOTAL RIG DAYRATE |  |  |  |  | 34947.235
MUD LOGGING - WEATHERFORD
Daily Operating Rate | 1664.7 | $ |  | 1 | 1664.7
Daily Stand by Rate | 200 | $ |  |  | 0
Mobilization unit MUD LOGGING
TOTAL COST MUD LOGGING |  |  |  |  | 1664.7
DOWNHOLE TOOLS
6'' BIT-CM34MRS-VAREL | 4850 | $ |  |  | 0
|  | $ |  |  | 0
|  | $ |  |  | 0
TOTAL COST DOWNHOLE TOOLS |  |  |  |  | 0
DRILLING MUD - NOS
Service Cost = senior mud eng. + mud eng. + mud lab =320+270+70= | 390 | $ |  | 1 | 390
Product cost |  | $ |  |  | 0
Mud lab transportation |  | $
TOTAL COST- DRILLING MUD |  |  |  |  | 390
SOLID CONTROL - NOS
operators service cost | 270 | $ |  |  | 0
centrifuge operating | 300 | $ |  |  | 0
centrifuge stand by | 150 | $ |  |  | 0
TOTAL COST SOLID CONTROL |  |  |  |  | 0
TOTAL COST- DRILLING MUD & SOLID CONTROL |  |  |  |  | 390
WELL HEAD MSP DRILEX
Csg Head Spool 13"5/8*5000 MSP/DRILEX | 4820 | $ |  |  | 0
|  | $ |  |  | 0
|  | $ |  |  | 0
TOTAL COST WELL HEAD |  |  |  |  | 0
COMMUNICATION AND DATA
VSAT rental | 120 | $ |  | 1 | 120
TOTAL COMMUNICATION |  |  |  |  | 120
CASING
102 Joints 7" Casing 32# TENARIS ( 1178.32 m). | 136.28 | $ |  |  | 0
Casing Transport | 16280 | $ |  |  | 0
TOTAL COST CASING |  |  |  |  | 0
CASING ACCESSORIES - WEATHERFORD
7" Liner Assembly | 72350 | $ |  |  | 0
service operation | 54500 | $ |  |  | 0
TOTAL COST ACCESSORIES CASING |  |  |  |  | 0
RUNNING CASING AND TUBING - WEATHERFORD
Service run casing 7" + JAM | 13007 | $ |  |  | 0
Crew & Equipment Mob/Demob | 4656 | $ |  |  | 0
TOTAL COST RUNNING CASING & TUBING |  |  |  |  | 0
logging
Logging Unit Stand by | 2500 | $ |  |  | 0
RUN 01 (DLL-MSFL-WSTT-IDT-ICT-GR) | 423230.44 | $ |  |  | 0
RUN 02 (SDLT-DSNT-CSNG)
RUN 03 (GR-XRMI)
RUN 04 (GR-CBL/VDL)
RUN 05 (GR-VSP)
RUN 06 (GR-RDT)
0
CEMENTING CASING AND TUBING TESTING & COMPLETION - SCHLUMBERGER
Pers & cmt eqpt daily rate std by while operating | 1270 | $ |  | 1 | 1270
Cementing 7" Liner products | 156677.6 | $ |  |  | 0
Well testing equipement test & Flare Lines | 4750 | $ |  | 1 | 4750
TOTAL COST CEMENTING CASING & TUBING |  |  |  |  | 6020
RIG SUPERVISION
Drilling Supervision | 3500 | $ |  | 1 | 3500
TOTAL COST RIG SUPERVISION |  |  |  |  | 3500
WATER SUPPLIED WITH OLD DISTANCE & OLD COST SINCE SEPT/02 TO SEPT 14 /2013 -MARAR
0
TOTAL COST OF WATER |  |  |  |  | 0
WATER SUPPLIED WITH NEW DISTANCE AND NEW COST - MARAR
Water truck for camp 20 m3 | 2 | $ | 400 | 1 | 800
Water truck for Rig 20 m3 | 1.54 | $ | 400 | 1 | 616
TOTAL COST WATER SUPPLIED BASED ON NEW DISTANCE AND NEW COST |  |  |  |  | 1416
WATER SERVICES - NAZAR
Provide package for water well 1 + water well 2 on stand by ( 1200+269 ) | 1469 | $ |  | 1 | 1469
TOTAL COST WATER SERVICES |  |  |  |  | 1469
SECURITY
Watch man | 80 | $ |  | 12 | 960
Equipement | 400 | $ |  | 1 | 400
TOTAL COST SECURITY |  |  |  |  | 1360
Daily cost |  |  |  |  | 50886.935
Note on G2: rep0234: Rig Camp moved 20th August Main Camp, Rig Site Camp and Watchmen Camp operative 24th…Rig move will begin 25th.